## CPM Worksheets
CPM Worksheet
2101981.0128
Project: Joe's Crab Shack
Architect: GPD Group | [8 empty] | 43.7%
SOV# | Activity ID | ACTIVITY DESCRIPTION/ ESTIMATE ITEMS | DURATION |  |  |  |  | MATERIAL |  | LABOR |  | EQUIPMENT | SUBCONTRACT |  |  |  | DIRECT ACTIVITY COST | PRORATE AMOUNT | ACTIVITY VALUE
|  |  | CALCULATED (DAYS) | Ref. | Duration |  | % USED ON ACTIVITY | ESTIMATE COST | SALES TAX | ESTIMATE COST | LABOR BURDEN | ESTIMATE COST | ESTIMATE COST | Sub Markup | Sub Insurance | % Cost Used
|  |  |  | Page # | Calc. | Adjust |  |  | 7% |  | 30.06% |  |  | 30% | 0.3% |  |  | 0.1728%
16 | A1001 | Mobilization |  | JOH | 5 | 5 | 100% | 84523 | 5916.61 | [7 empty] | 90439.61 | 15626.1558 | 106065.7658
0
0
1 | A1005 | Erosion Control |  |  | 1.7214 | 1 | 100% | [5 empty] | 29255.139 |  |  |  | 13560.0447 | 2342.9045 | 15902.9493
|  | Silt Fence |  |  | 0.32125 |  | 100% | [5 empty] | 208.427 | 270.9551 | 0.81287 | 100% | 271.768 | 46.9561
|  | Stone |  |  | 1.1083 |  | 20% | [5 empty] | 23569.4177 | 30640.243 | 91.9207 | 20% | 6146.4327 | 1061.9806
|  | Temporary Seeding |  |  | 0.086172 |  | 100% | [5 empty] | 264.4626 | 343.8013 | 1.0314 | 100% | 344.8327 | 59.5802
|  | Hay Bales |  |  | 0.2056 |  | 100% | [5 empty] | 5212.8317 | 6776.6813 | 20.33 | 100% | 6797.0113 | 1174.3876
[14 empty] | 0 | 0 |  |  | 0
1 | A1010 | Clear and Grub |  |  | 0.53753 | 1 | 100% | [5 empty] | 1275.6767 | 1658.3797 | 4.9751 | 100% | 2939.0316 | 507.8059 | 3446.8375
[14 empty] | 0 | 0 |  |  | 0
1 | A1020 | Strip and Stock |  |  | 0.18565 | 1 | 100% | [5 empty] | 278.3669 | 361.8769 | 1.0856 | 100% | 641.3294 | 110.8089 | 752.1383
[14 empty] | 0 |  |  |  | 0
1 | A1030 | Building Pad |  |  | 5.9812 | 6 | 100% | [5 empty] | 55903.9462 |  |  | 100% | 72893.1555 | 12594.4794 | 85487.6349
|  | Site Cut |  |  | 0.6 |  | 100% | [5 empty] | 84.24 | 109.512 | 0.32854 | 100% | 109.8405 | 18.9782
|  | Site Fill |  |  | 5.3812 |  | 100% | [5 empty] | 55819.7062 | 72565.6181 | 217.6969 | 100% | 72783.315 | 12575.5012
[14 empty] | 0 | 0 |  |  | 0
15 | A1031 | UnderGround Water & Sanitary |  |  | 4.038 | 5 | 100% | [5 empty] | 24876.32 | 32339.216 | 97.0176 | 100% | 32436.2336 | 5604.3324 | 38040.5661
|  | 4" PVC |  |  | 0.2 |  | 100% | [5 empty] | 477.74 | 621.062 | 1.8632 | 100% | 622.9252 | 107.629
|  | 6" PVC |  |  | 0.323 |  | 100% | [5 empty] | 1208.74 | 1571.362 | 4.7141 | 100% | 1576.0761 | 272.3144
|  | 45 degree bend |  |  | 0.04 |  | 100% | [5 empty] | 219.1 | 284.83 | 0.85449 | 100% | 285.6845 | 49.3606
|  | 90 degree bend |  |  | 0.35 |  | 100% | [5 empty] | 2028.39 | 2636.907 | 7.9107 | 100% | 2644.8177 | 456.9716
|  | Cleanout |  |  | 1.5 |  | 100% | [5 empty] | 830.92 | 1080.196 | 3.2406 | 100% | 1083.4366 | 187.1962
|  | Grease Trap |  |  | 0.375 |  | 100% | [5 empty] | 3059.78 | 3977.714 | 11.9331 | 100% | 3989.6471 | 689.3312
|  | Plugs |  |  | 0.25 |  | 100% | [5 empty] | 166.55 | 216.515 | 0.64955 | 100% | 217.1645 | 37.5217
|  | Backflow Preventer |  |  | 1 |  | 100% | [5 empty] | 16885.1 | 21950.63 | 65.8519 | 100% | 22016.4819 | 3804.0077
[14 empty] | 0 | 0 |  |  | 0
14 | A1032 | Underground Elecrtrical |  |  | 3 | 3 | 20% | [5 empty] | 137940 | 179322 | 537.966 | 20% | 35971.9932 | 6215.241 | 42187.2342
0
1 | A1040 | Footing Excavation |  |  | 5.119 | 5 | 100% | [5 empty] | 9023 | 11729.9 | 35.1897 |  | 11765.0897 | 2032.7722 | 13797.8619
|  | Machine |  |  | 3.354 |  | 100% | [5 empty] | 8527 | 11085.1 | 33.2553 | 100% | 11118.3553 | 1921.0294
|  | Hand |  |  | 1.765 |  | 100% | [5 empty] | 496 | 644.8 | 1.9344 | 100% | 646.7344 | 111.7428
[14 empty] | 0 | 0 |  | 0 | 0
2 | A1050 | Footing Rebar |  |  | 6.954 | 3 | 50% | [5 empty] | 19015.8 | 24720.54 | 74.1616 | 50% | 12397.3508 | 2142.0143 | 14539.3651
[14 empty] | 0 | 0 |  |  | 0
2 | A1060 | Pour Footings |  |  | 3.252 | 2 | 50% | [5 empty] | 41273.3 | 53655.29 | 160.9659 | 50% | 26908.1279 | 4649.1863 | 31557.3143
[14 empty] | 0 | 0 |  |  | 0
2 | A1062 | Form Foundation Walls |  |  | 14 | 9 | 50% | [5 empty] | 24016 | 31220.8 | 93.6624 | 75% | 23485.8468 | 4057.8846 | 27543.7314
[14 empty] | 0 | 0 |  |  | 0
2 | A1070 | Foundation Wall Rebar |  |  | 6.954 | 2 | 50% | [5 empty] | 19015.8 | 24720.54 | 74.1616 | 50% | 12397.3508 | 2142.0143 | 14539.3651
[14 empty] | 0 | 0 |  |  | 0
2 | A1080 | Pour Foundation Walls |  |  | 3.252 | 2 | 50% | [5 empty] | 41273.3 | 53655.29 | 160.9659 | 50% | 26908.1279 | 4649.1863 | 31557.3143
[14 empty] | 0 | 0 |  |  | 0
1 | A1091 | Granular Fill |  |  | 1.1083 | 1 | 80% | [5 empty] | 23569.4177 | 30640.243 | 91.9207 | 80% | 24585.731 | 4247.9226 | 28833.6536
[14 empty] | 0 | 0 |  |  | 0
2 | A1100 | Slab Vapor Barrier |  |  | 3.38 | 2 | 100% | [5 empty] | 9000.48 | 11700.624 | 35.1019 | 100% | 11735.7259 | 2027.6987 | 13763.4246
0
2 | A1101 | Termite Treatment |  |  | 4.063 | 1 | 100% | [5 empty] | 3882 | 5046.6 | 15.1398 | 100% | 5061.7398 | 874.5674 | 5936.3072
[14 empty] | 0 | 0 |  |  | 0
2 | A1110 | Form Slab Edges |  |  | 14 | 3 | 25% | [5 empty] | 24016 | 31220.8 | 93.6624 | 25% | 7828.6156 | 1352.6282 | 9181.2438
[14 empty] | 0 | 0 |  |  | 0
2 | A1120 | Slab Reinforcing |  |  | 1.352 | 2 | 100% | [5 empty] | 2458.65 | 3196.245 | 9.5887 | 100% | 3205.8337 | 553.904 | 3759.7377
[14 empty] | 0 | 0 |  | 0 | 0
13 | A1121 | Mechanical Sleves |  |  | 5 | 5 | 2% | [5 empty] | 147085 | 191210.5 | 573.6315 | 2% | 3835.6826 | 662.7292 | 4498.4119
[14 empty] | 0 | 0 |  | 0 | 0
14 | A1122 | Electrical Sleeves |  |  | 5 | 5 | 2% | [5 empty] | 137940 | 179322 | 537.966 | 2% | 3597.1993 | 621.5241 | 4218.7234
[14 empty] | 0 | 0 |  | 0 | 0
15 | A1123 | Plumbing Sleeves |  |  | 5 | 5 | 2% | [5 empty] | 101359 | 131766.7 | 395.3001 | 2% | 2643.24 | 456.699 | 3099.939
[14 empty] | 0 | 0 |  | 0 | 0
2 | A1130 | Pour Slab |  |  | 1.007 | 1 | 80% | [5 empty] | 22792 | 29629.6 | 88.8888 | 80% | 23774.791 | 4107.8084 | 27882.5994
[14 empty] | 0 | 0 |  | 0 | 0
2 | A1140 | Concrete Finshes |  |  | 2.74 | 2 | 100% | [6 empty] | 0 | 0 |  | 5543.0875 | 957.7347 | 6500.8222
|  | Smooth Formed |  |  | 1.74 | [7 empty] | 2466.9 | 3206.97 | 9.6209 | 100% | 3216.5909 | 555.7626
|  | Troweled and Broom |  |  | 1 | [7 empty] | 1784.26 | 2319.538 | 6.9586 | 100% | 2326.4966 | 401.9721
[14 empty] | 0 | 0 |  | 0 | 0
2 | A1150 | Slab Joints |  |  | 1 | 1 | 100% | [5 empty] | 916.69 | 1191.697 | 3.5751 | 100% | 1195.2721 | 206.5191 | 1401.7912
[14 empty] | 0 | 0 |  | 0 | 0
2 | A1160 | Forms stairs & Ramps |  |  | 14 | 2 | 25% | [5 empty] | 24016 | 31220.8 | 93.6624 | 25% | 7828.6156 | 1352.6282 | 9181.2438
[14 empty] | 0 | 0 |  | 0 | 0
2 | A1170 | Pour Stairs and Ramps |  |  | 1 | 1 | 20% | [5 empty] | 22792 | 29629.6 | 88.8888 | 20% | 5943.6978 | 1026.9521 | 6970.6499
[14 empty] | 0 | 0 |  | 0 | 0
3 | A1180 | CMU Block Walls |  |  | 10.099 | 7 | 100% | [7 empty] | 0 | 100% | 25704.8238 | 4441.2795 | 30146.1033
|  | Grout |  |  | 2.875 | [7 empty] | 4405.5 | 5727.15 | 17.1815 | 100% | 5744.3315 | 992.5056
|  | Block |  |  | 7.224 | [7 empty] | 15308.3 | 19900.79 | 59.7024 | 100% | 19960.4924 | 3448.7739
[14 empty] | 0 | 0 |  | 0 | 0
4 | A1189 | Steel Columns |  |  | 2.2382 | 4 | 100% | [5 empty] | 42521.5 | 55277.95 | 165.8339 | 100% | 55443.7839 | 9579.577 | 65023.3608
[14 empty] | 0 | 0 |  | 0 | 0
3 | A1190 | Brick front and right elevation |  |  | 69.152 | 14 | 50% | [6 empty] | 0 | 0 | 50% | 122027.7177 | 21083.9491 | 143111.6668
|  | Brick |  |  | 27.14 |  | 50% | [5 empty] | 68597.3 | 89176.49 | 267.5295 | 50% | 44722.0097 | 7727.0688
|  | Anchor bolts |  |  | 11.512 |  | 50% | [5 empty] | 101175.21 | 131527.773 | 394.5833 | 50% | 65961.1782 | 11396.7724
|  | scaffolding |  |  |  |  | 50% | [5 empty] | 600 | 780 | 2.34 | 50% | 391.17 | 67.5864
|  | Misc. Items |  |  | 27 |  | 50% | [5 empty] | 14743.62 | 19166.706 | 57.5001 | 50% | 9612.1031 | 1660.7792
|  | Mortar |  |  | 3.5 |  | 50% | [5 empty] | 2057.3 | 2674.49 | 8.0235 | 50% | 1341.2567 | 231.7423
[14 empty] | 0 | 0 |  | 0 | 0
3 | A1191 | Brick Back and Left Elevation |  |  | 69.152 | 14 | 50% | [5 empty] | 187173.43 | 243325.459 | 729.9764 | 50% | 122027.7177 | 21083.9491 | 143111.6668
|  | Brick |  |  | 27.14 |  | 50% | [5 empty] | 68597.3 | 89176.49 | 267.5295 | 50% | 44722.0097 | 7727.0688
|  | Anchor Bolts |  |  | 11.512 |  | 50% | [5 empty] | 101175.21 | 131527.773 | 394.5833 | 50% | 65961.1782 | 11396.7724
|  | Scaffolding |  |  |  |  | 50% | [5 empty] | 600 | 780 | 2.34 | 50% | 391.17 | 67.5864
|  | Misc. Items |  |  | 27 |  | 50% | [5 empty] | 14743.62 | 19166.706 | 57.5001 | 50% | 9612.1031 | 1660.7792
|  | Mortar |  |  | 3.5 |  | 50% | [5 empty] | 2057.3 | 2674.49 | 8.0235 | 50% | 1341.2567 | 231.7423
[14 empty] | 0 | 0 |  | 0 | 0
3 | A1192 | Cast Stone |  |  | 4.51 | 7 | 100% | [5 empty] | 7771.79 | 10103.327 | 30.31 | 100% | 10133.637 | 1750.8898 | 11884.5268
[14 empty] | 0 | 0 |  | 0 | 0
4 | A1210 | Structural Steel |  |  | 0.637 | 5 | 100% | [5 empty] | 18805.3 | 24446.89 | 73.3407 | 100% | 24520.2307 | 4236.6055 | 28756.8361
[14 empty] | 0 | 0 |  | 0 | 0
4 | A1220 | Metal Stud Framing |  |  | 0.737 | 3 | 100% | [5 empty] | 304.98 | 396.474 | 1.1894 | 100% | 397.6634 | 68.7083 | 466.3717
[14 empty] | 0 | 0 |  | 0 | 0
4 | A1221 | Misc. Steel |  |  | 3.414 | 3 | 100% | [5 empty] | 11287.365 | 14673.5745 | 44.0207 | 100% | 14717.5952 | 2542.9061 | 17260.5013
[14 empty] | 0 | 0 |  | 0 | 0
5 | A1240 | Roof Trusses |  |  | 3.38 | 7 | 100% | [5 empty] | 31037.7 | 40349.01 | 121.047 | 100% | 40470.057 | 6992.4165 | 47462.4735
[14 empty] | 0 | 0 |  | 0 | 0
5 | A1250 | Wood low roof framing |  |  | 3.29 | 4 | 100% | [5 empty] | 7315.865 | 9510.6245 | 28.5319 |  | 9539.1564 | 1648.1754 | 11187.3318
|  | 2x10 |  |  | 1.3 | [7 empty] | 4014.95 | 5219.435 | 15.6583 | 100% | 5235.0933 | 904.5194
|  | 2x8 |  |  | 1.01 | [7 empty] | 727.64 | 945.932 | 2.8378 | 100% | 948.7698 | 163.9284
|  | Blocking |  |  | 0.98 | [7 empty] | 2323.7 | 3020.81 | 9.0624 | 100% | 3029.8724 | 523.5014
|  | Wood Cap |  |  | 0.621 | [7 empty] | 249.575 | 324.4475 | 0.97334 | 100% | 325.4208 | 56.2262
[14 empty] | 0 | 0 |  | 0 | 0
5 | A1260 | Wall Framing |  |  | 13.06 | 10 | 100% | [5 empty] | 9339.33 | 12141.129 | 36.4234 |  | 12177.5524 | 2104.0375 | 14281.5899
|  | 2x10 |  |  | 1.3 | [7 empty] | 5668.01 | 7368.413 | 22.1052 | 100% | 7390.5182 | 1276.9337
|  | 2x8 |  |  | 0.6 | [7 empty] | 3671.32 | 4772.716 | 14.3181 | 100% | 4787.0341 | 827.1038
|  | Wall Sheathing |  |  | 11.16 | [12 empty] | 0
[14 empty] | 0 | 0 |  | 0 | 0
6 | A1261 | Building Wrap |  |  | 2.116 | 2 | 100% | [5 empty] | 1418.43 | 1843.959 | 5.5319 | 100% | 1849.4909 | 319.555 | 2169.0459
[14 empty] | 0 | 0 |  | 0 | 0
5 | A1270 | Headers |  |  | 1.35 | 3 | 100% | [5 empty] | 3534.23 | 4594.499 | 13.7835 |  | 4608.2825 | 796.219 | 5404.5015
|  | 2x6 |  |  | 0.43 | [7 empty] | 269.46 | 350.298 | 1.0509 | 100% | 351.3489 | 60.7061
|  | 2x8 |  |  | 0.45 | [7 empty] | 662.22 | 860.886 | 2.5827 | 100% | 863.4687 | 149.1901
|  | 2x0 |  |  | 0.47 | [7 empty] | 2602.55 | 3383.315 | 10.1499 | 100% | 3393.4649 | 586.3229
[14 empty] | 0 | 0 |  | 0 | 0
5 | A1280 | Wood Decking |  |  | 7.5 | 6 | 100% | [5 empty] | 33972.9 | 44164.77 | 132.4943 | 100% | 44297.2643 | 7653.6813 | 51950.9456
[14 empty] | 0 | 0 |  | 0 | 0
6 | A1290 | Rigid Insulation |  |  | 8.867 | 4 | 50% | [5 empty] | 900.48 | 1170.624 | 3.5119 | 50% | 587.0679 | 101.4336 | 688.5015
[14 empty] | 0 | 0 |  | 0 | 0
15 | A1300 | In Wall Plumbing |  |  |  | 7 | 30% | [5 empty] | 101359 | 131766.7 | 395.3001 | 30% | 39648.6 | 6850.4851 | 46499.0851
[14 empty] | 0 | 0 |  | 0 | 0
13 | A1301 | In Wall HVAC |  |  |  | 7 | 30% | [5 empty] | 147085 | 191210.5 | 573.6315 | 30% | 57535.2394 | 9940.9387 | 67476.1781
[14 empty] | 0 | 0 |  | 0 | 0
14 | A1302 | In Wall Electrical |  |  |  | 7 | 30% | [5 empty] | 137940 | 179322 | 537.966 | 30% | 53957.9898 | 9322.8615 | 63280.8513
[14 empty] | 0 | 0 |  | 0 | 0
6 | A1310 | Roof Sheathing |  |  | 4.43 | 5 | 100% | [5 empty] | 9404.42 | 12225.746 | 36.6772 | 100% | 12262.4232 | 2118.7015 | 14381.1247
[14 empty] | 0 | 0 |  | 0 | 0
6 | A1320 | Roof Inuslation |  |  | 8.867 | 5 | 50% | [5 empty] | 900.48 | 1170.624 | 3.5119 | 100% | 1174.1359 | 202.8672 | 1377.0031
[14 empty] | 0 | 0 |  | 0 | 0
6 | A1330 | Membrane Roofing |  |  | 2.007 | 5 | 100% | [5 empty] | 10945.464 | 14229.1032 | 42.6873 | 100% | 14989.1493 | 2589.8252 | 17578.9746
|  | Flashing |  |  | 1.678 | [7 empty] | 550.164 | 715.2132 | 2.1456 | 100% | 717.3588 | 123.9453
[14 empty] | 0 | 0 |  | 0 | 0
3 | A1349 | Masonry Cleaing |  |  | 6.7 | 4 | 100% | [5 empty] | 5735.2 | 7455.76 | 22.3673 | 100% | 7478.1273 | 1292.0708 | 8770.1981
[14 empty] | 0 | 0 |  | 0 | 0
4 | A1350 | Exterior Canopies |  |  | 4.781 | 5 | 100% | [5 empty] | 31686.9 | 41192.97 | 123.5789 | 100% | 41316.5489 | 7138.6733 | 48455.2222
[14 empty] | 0 | 0 |  | 0 | 0
4 | A1360 | Install Handrails |  |  | 2.883 | 3 | 100% | [5 empty] | 75438.8 | 98070.44 | 294.2113 | 100% | 98364.6513 | 16995.4445 | 115360.0958
[14 empty] | 0 | 0 |  | 0 | 0
11 | A1370 | Install Gyp board and Cement board |  |  | 10.119 | 12 | 100% | [5 empty] | 9140.19 | 11882.247 | 35.6467 |  | 11917.8937 | 2059.1737 | 13977.0674
|  | Gypsum Board |  |  | 0.671 | [7 empty] | 599.07 | 778.791 | 2.3364 | 100% | 781.1274 | 134.9632
|  | Cement Board |  |  | 9.448 | [7 empty] | 8541.12 | 11103.456 | 33.3104 | 100% | 11136.7664 | 1924.2105
[14 empty] | 0 | 0 |  | 0 | 0
11 | A1380 | RFP Panels |  |  | 5.188 | 5 | 100% | [5 empty] | 6112.95 | 7946.835 | 23.8405 | 100% | 7970.6755 | 1377.1733 | 9347.8488
[14 empty] | 0 | 0 |  | 0 | 0
11 | A1382 | Groove Panels |  |  | 0.289 | 5 | 100% | [5 empty] | 349.457 | 454.2941 | 1.3629 | 100% | 455.657 | 78.7284 | 534.3854
[14 empty] | 0 | 0 |  | 0 | 0
11 | A1400 | Acoustical Ceiling |  |  | 3.246 | 4 | 100% | [5 empty] | 3113.46 | 4047.498 | 12.1425 | 100% | 4059.6405 | 701.4247 | 4761.0652
[14 empty] | 0 | 0 |  | 0 | 0
5 | A1410 | Wood Trim |  |  | 7.86 | 7 | [6 empty] | 12733.4 | 16553.42 | 49.6603 | 100% | 16603.0803 | 2868.6802 | 19471.7605
[14 empty] | 0 | 0 |  | 0 | 0
9 | A1430 | Bathroom Tile |  |  | 4.116 | 4 | 100% | [5 empty] | 3989.76 | 5186.688 | 15.5601 | 100% | 5202.2481 | 898.8444 | 6101.0925
[14 empty] | 0 | 0 |  | 0 | 0
15 | A1431 | Bathroom Fixutres |  |  |  | 5 | 20% | [5 empty] | 101359 | 131766.7 | 395.3001 | 20% | 26432.4 | 4566.9901 | 30999.3901
[14 empty] | 0 | 0 |  | 0 | 0
9 | A1440 | Porcelain Plank Tile |  |  | 8.652 | 8 | 100% | [5 empty] | 16895.6 | 21964.28 | 65.8928 | 100% | 22030.1728 | 3806.3733 | 25836.5461
[14 empty] | 0 | 0 |  | 0 | 0
9 | A1450 | Quarry Tile |  |  | 10.68 | 11 | 100% | [5 empty] | 15208.1 | 19770.53 | 59.3116 | 100% | 19829.8416 | 3426.2 | 23256.0416
[14 empty] | 0 | 0 |  | 0 | 0
9 | A1451 | Porcelain Concrete |  |  | 3.36 | 4 | 100% | [5 empty] | 3568.861 | 4639.5193 | 13.9186 | 100% | 4653.4379 | 804.021 | 5457.4589
[14 empty] | 0 | 0 |  | 0 | 0
8 | A1460 | Install Hollow Metal Frames |  |  | 1 | 1 | 100% | 2464.8 | 172.536 | 352.8 | 107.9568 |  |  | 0 | 0 |  | 3098.0928 | 535.2885 | 3633.3813
[14 empty] | 0 | 0 |  | 0 | 0
8 | A1470 | Hang Doors |  |  | 3.785 | 3 | 100% | [6 empty] | 0 | 0 |  | 22507.99 | 3888.9305 | 26396.9205
|  | Hollow Metal Doors |  |  | 0.235 |  | 100% | 1684.3 | 117.901 | 83.012 | 25.4017 |  |  | 0 | 0 |  | 1910.6147 | 330.116
|  | Wood Doors |  |  | 0.8 |  | 100% | 4128.6 | 289.002 | 282.24 | 86.3654 |  |  | 0 | 0 |  | 4786.2074 | 12911.4572
|  | Eliason Doors |  |  | 0.5 |  | 100% | 3081 | 215.67 | 176.4 | 53.9784 |  |  | 0 | 0 |  | 3527.0484 | 12911.4572
|  | Hardware |  |  | 2.25 |  | 100% | 10508.8 | 735.616 | 793.8 | 242.9028 |  |  | 0 | 0 |  | 12281.1188 | 12911.4572
[10 empty] | 1335.452 | 408.6483 |  |  | 0 | 0 |  |  | 0
8 | A1480 | Install Windows |  |  | 4.3 | 4 | 100% | [6 empty] | 0 | 0 |  | 52291.0492 | 9034.8475 | 61325.8967
|  | Window |  |  | 1.7 |  |  | 6146.5 | 430.255 | 599.76 | 183.5266 |  |  | 0 | 0 |  | 7360.0416 | 1271.668
|  | Wood Clad |  |  | 2.6 |  |  | 40872 | 2861.04 | 917.28 | 280.6877 |  |  | 0 | 0 |  | 44931.0077 | 7763.1795
[10 empty] | 1517.04 | 464.2142 |  |  | 0 | 0 |  | 0 | 0
10 | A1489 | Paint Walls |  |  | 4.668 | 5 | 100% | [5 empty] | 4180.14 | 5434.182 | 16.3025 | 100% | 5450.4845 | 941.7347 | 6392.2193
[14 empty] | 0 | 0 |  | 0 | 0
10 | A1490 | Paint Doors |  |  | 1.8 | 1 | 100% | [5 empty] | 337.428 | 438.6564 | 1.316 | 100% | 439.9724 | 76.0184 | 515.9908
[14 empty] | 0 | 0 |  | 0 | 0
7 | A1500 | Caulking |  |  | 9.378 | 5 | 100% | [5 empty] | 1750.06 | 2275.078 | 6.8252 | 100% | 2281.9032 | 394.2672 | 2676.1705
[14 empty] | 0 | 0 |  | 0 | 0
15 | A1510 | Interior Plumbing |  |  |  | 20 | 48% | [5 empty] | 101359 | 131766.7 | 395.3001 | 48% | 63288.41 | 10934.9715 | 74223.3815
[14 empty] | 0 | 0 |  | 0 | 0
13 | A1520 | Interior HVAC |  |  |  | 20 | 68% | [5 empty] | 147085 | 191210.5 | 573.6315 | 68% | 130413.2094 | 22532.7943 | 15296.838
[14 empty] | 0 | 0 |  | 0 | 0
14 | A1530 | Interior Electrical |  |  |  | 20 | 48% | [5 empty] | 137940 | 179322 | 537.966 | 48% | 86332.7837 | 14916.5784 | 101249.362
[14 empty] | 0 | 0 |  | 0 | 0
5 | A1540 | Wood Booths |  |  | 4 | 5 | 100% | [5 empty] | 9093.2 | 11821.16 | 35.4635 | 100% | 11856.6235 | 2048.5874 | 13905.2109
[14 empty] | 0 | 0 |  | 0 | 0
5 | A1550 | Install Bar |  |  | 2.667 | 3 | 100% | [5 empty] | 4754.4 | 6180.72 | 18.5422 | 100% | 6199.2622 | 1071.1085 | 7270.3707
[14 empty] | 0 | 0 |  | 0 | 0
12 | A1580 | Install Signage & Specialties |  |  | 1.583 | 4 | 100% | [6 empty] | 0 | 0 |  | 2284.2174 | 394.6671 | 2678.8845
|  | Fire Extinguishers |  |  | 1 |  |  | 1425.42 | 99.7794 | 176.4 | 53.9784 |  |  | 0 | 0 |  | 1755.5778 | 303.3287
|  | Signage |  |  | 0.083 |  |  | 52.2 | 3.654 | 14.7 | 4.4982 |  |  | 0 | 0 |  | 75.0522 | 12.9675
|  | Shelving |  |  | 0.5 |  |  | 316.26 | 22.1382 | 88.2 | 26.9892 |  |  | 0 | 0 |  | 453.5874 | 78.3708
[10 empty] | 279.3 | 85.4658 |  |  | 0 | 0 |  | 0 | 0
16 | A1590 | Final Cleaning |  |  |  | 5 | 100% | [5 empty] | 1500 | 1950 | 5.85 | 100% | 1955.85 | 337.9318 | 2293.7818
[14 empty] | 0 | 0 |  | 0 |  | 1964331.847
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 1792306.3258 | 309674.687 | 2101981.0128
[11 empty] | 27 |  |  | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 | 0 |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
[14 empty] | 0 |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
[8 empty] | 47018.5 | 3291.295 | 1517.04 | 464.2142 |  |  | 0 | 0 |  | 52291.0492
0

## EQ
Amount to Spread
| JOH Monthly Payments | 22285.2857
| Insurance | 15554
| Financing Cost | 11295
| General OH | 229529
| Profit | 63057
341720.2857
0
New Total Direct Cost |  |  | 0
| Project Cost | 2101909
| Amount to Spread | 309668
1792241
Prorate Amount % | Amount to Spread | 309668
| New Total Direct Cost | 1792241
17.28%